## Sprint 2 burndown chart
Sprint Tasks (Sprint Backlog) | Week 1 Oct. 25-31 | Week 2 Nov. 01-07 | Week 3 Nov. 08-14 | Week 4 Nov. 15-21 | Week 5 Nov. 22-24
UI Interface Implementation | 1 | 3 | 4.5 | 2.5 | 0
Csv Operator Implementation | 3 | 0 | 0 | 3.5 | 0
Table UI Setter Implementation | 0 | 7 | 0 | 2 | 0
Chart UI Setter Implementation | 2 | 1.5 | 0 | 3.5 | 0
Table Controllor Implementation | 3 | 5 | 8.5 | 1.5 | 0
Chart Controllor Implementation | 3 | 6.5 | 11.5 | 2 | 0
Additional Feature implementation | 0 | 3 | 15.5 | 11 | 3
Csv Operator Test | 0 | 2 | 0 | 4 | 0
Table Controllor Test | 0 | 0 | 0 | 2 | 1.5
Chart Controllor Test | 0 | 0 | 0 | 2 | 2
Total hours | 12 | 28 | 40 | 34 | 6.5
Left hours | 108.5 | 80.5 | 40.5 | 6.5 | 0